crypto-mvp

Dashboard Frontend — Development Roadmap

Sprint-by-sprint build plan  ·  React + Recharts + Tailwind

# Overview

This roadmap breaks the dashboard frontend build into six sprints. Each sprint produces runnable, reviewable output. No sprint should be considered complete until its exit criteria are fully met.

The dashboard is a React SPA served from the existing FastAPI backend at localhost:8000. It connects to 10 read-only endpoints and is packaged as a native desktop window using PyWebView. It must require no browser tab, no login, and must default to dark mode.

| Sprint | Focus | Duration | Gate |
| --- | --- | --- | --- |
| 1 | Project scaffold, tooling & design system | 2–3 days | App shell renders with nav and mock data |
| 2 | Core data layer — API hooks and state | 2–3 days | All 10 endpoints polled, typed, error-handled |
| 3 | Overview + System Health views | 2–3 days | Both views live with real backend data |
| 4 | Market Data + Fills + PnL views | 3–4 days | All chart views render accurate data |
| 5 | Settings view, polish, accessibility | 1–2 days | App meets all design spec requirements |
| 6 | PyWebView packaging + launch script | 1–2 days | One-command launch on Windows 10/11 |

| Sprint 1 ● 2–3 days Project Scaffold, Tooling & Design System | FIRST TO BUILD |
| --- | --- |

Set up the entire frontend project from scratch. By the end of Sprint 1 the app shell runs in the browser with navigation, dark theming, and realistic mock data — no real API calls yet. This sprint is about speed: get the skeleton right so all later sprints can move fast.

### Objectives

- Vite + React project initialized inside apps/dashboard/frontend/

- Tailwind CSS configured for dark mode (class strategy)

- JetBrains Mono + Inter loaded via Google Fonts

- 6-view layout with icon sidebar navigation working

- All 9 reusable component primitives built with mock data

- Global dark theme tokens established (background, card, accent colors)

### Task Breakdown

| Task | Priority | Complexity | Output |
| --- | --- | --- | --- |
| Vite + React + Tailwind project init | High | Low | package.json, vite.config.js |
| Tailwind dark config + global CSS tokens | High | Low | index.css, tailwind.config.js |
| App.jsx shell with sidebar nav + routing | High | Med | App.jsx, 6 empty view stubs |
| Header component (logo, status strip placeholder) | High | Low | Header.jsx |
| StatusDot component | High | Low | components/common/StatusDot.jsx |
| MetricCard component | High | Low | components/common/MetricCard.jsx |
| PriceDisplay component (monospace, sign color) | High | Low | components/common/PriceDisplay.jsx |
| SideTag component (BUY blue / SELL orange) | Med | Low | components/common/SideTag.jsx |
| DataTable component (sortable, dark styled) | High | Med | components/common/DataTable.jsx |
| TimeAgo component | Med | Low | components/common/TimeAgo.jsx |
| LoadingState + ErrorState components | Med | Low | components/common/Loading.jsx |
| ChartContainer wrapper with title + timestamp | High | Low | components/charts/ChartContainer.jsx |
| Wire up all 6 routes with mock data in Overview | High | Med | views/Overview.jsx (mock) |

✓ Exit Criteria npm run dev boots without errors All 6 views reachable via sidebar nav Dark background (#0f1117) renders correctly Overview view shows all panels with mock data All 9 component primitives render in isolation

| Sprint 2 ● 2–3 days Data Layer — API Hooks & State Management | DEPENDENCY FOR ALL VIEWS |
| --- | --- |

Build the complete data layer before any more views. Every view in Sprint 3 and 4 imports from these hooks. Getting typing, error handling, and polling right here saves rework later. No new views this sprint — just a robust, tested data foundation.

### Endpoints to Cover

| Endpoint | Endpoint |
| --- | --- |
| /health | /funding |
| /positions | /order-books |
| /fills | /risk-events |
| /pnl | /alerts |
| /ticks | /kpis |

### Task Breakdown

| Task | Priority | Complexity | Output |
| --- | --- | --- | --- |
| useApi.js — generic polling hook with interval | High | Med | hooks/useApi.js |
| Error boundary: stale indicator + retry logic | High | Med | Part of useApi.js |
| useHealth.js (health + risk events + alerts) | High | Low | hooks/useHealth.js |
| usePosition.js (positions endpoint) | High | Low | hooks/usePosition.js |
| useFills.js (fills endpoint) | High | Low | hooks/useFills.js |
| usePnL.js (pnl + kpis endpoints) | High | Low | hooks/usePnL.js |
| useMarket.js (ticks + funding + order-books) | High | Low | hooks/useMarket.js |
| Decimal formatter utility (NUMERIC strings) | High | Low | utils/format.js |
| UTC-to-local timestamp formatter | Med | Low | utils/format.js |
| CORS proxy config for dev (localhost:5173 → 8000) | High | Low | vite.config.js proxy |
| Smoke test: log all 10 endpoint responses to console | High | Low | Dev validation only |

✓ Exit Criteria All 10 endpoints called successfully against live backend Polling refreshes every 10 seconds without page reload Stale/error state shows correctly when backend is down NUMERIC decimal values formatted correctly (2dp USD, 8dp BTC) Timestamps display in local time

| Sprint 3 ● 2–3 days Overview & System Health Views | FIRST LIVE VIEWS |
| --- | --- |

Build the two highest-value views first: Overview (default landing screen) and System Health (operational observability). These two views expose the most critical system state and will be used constantly during trading sessions.

### Overview View — Panels

- System Status Bar — colored dots for Collector, Paper Trader, DB; time-since-last-tick

- Position Summary card — XBT qty/side, entry price, mark price, unrealized PnL, position age

- PnL Summary card — realized PnL, fees paid, net PnL, fill count

- Recent Fills table — last 10 fills, timestamp / BUY+SELL tag / price / qty / fee

- Active Alerts card — firing alerts with severity; empty state "No active alerts"

### System Health View — Panels

- Collector Health block — cycles/hr, missing data rate, last 10 cycle results

- Paper Trader Health block — iterations/hr, error rate, last 10 results

- Risk Events table — all events newest first, type / severity / details

- Alert Log table — all evaluations, fired yes/no, details

### Task Breakdown

| Task | Priority | Complexity | Output |
| --- | --- | --- | --- |
| SystemStatusBar component (connects to /health) | High | Med | panels/SystemStatusBar.jsx |
| PositionSummary card (connects to /positions) | High | Med | panels/PositionSummary.jsx |
| PnLSummary card (connects to /pnl) | High | Low | panels/PnLSummary.jsx |
| RecentFills mini table (connects to /fills) | High | Med | panels/RecentFills.jsx |
| ActiveAlerts card (connects to /alerts) | High | Med | panels/ActiveAlerts.jsx |
| Overview.jsx — compose all panels, layout | High | Med | views/Overview.jsx |
| CollectorHealth block (derives from /health, /ticks) | High | Med | panels/CollectorHealth.jsx |
| PaperTraderHealth block | High | Med | panels/PaperTraderHealth.jsx |
| RiskEventsTable (connects to /risk-events) | High | Low | panels/RiskEventsTable.jsx |
| AlertLogTable (connects to /alerts) | Med | Low | panels/AlertLogTable.jsx |
| Health.jsx — compose all panels | High | Low | views/Health.jsx |
| Stale data warning: order book > 120s flagged | High | Low | Part of status logic |

✓ Exit Criteria Overview renders all 5 panels with live backend data System status dots correctly reflect live/stale state Unrealized PnL shows green/red based on sign Health view renders with live risk events and alert log Both views auto-refresh every 10 seconds

| Sprint 4 ● 3–4 days Market Data, Fills & PnL Views | CHART-HEAVY SPRINT |
| --- | --- |

The three data-exploration views. These are the most chart-heavy part of the build. Recharts setup, data transformation, and correct rendering of financial time series are the main challenges. Budget extra time here for chart tuning.

### Market Data View

- Mid Price line chart — last 2 hours, bid/ask overlay as dotted lines

- Bid/ask shaded band from order-books endpoint

- Market Data table — last 20 order book snapshots, spread/spread_bps

- Funding Rate bar chart — 24 hours, green/red bars by sign

### Fills View

- Fill Rate bar chart — fills per hour last 24h, split BUY (blue) / SELL (orange)

- Fill History table — all fills, sortable, color-coded SideTag

- Fill Statistics sidebar — totals, ratios, avg prices, volume, fees

### PnL View

- Cumulative PnL line chart — zero baseline, green fill above / red fill below

- Per-fill PnL breakdown table — realized_pnl, fee_paid, net_pnl per fill

- KPI cards — net annualized return, max drawdown, spread capture, fill rate, avg bps

### Task Breakdown

| Task | Priority | Complexity | Output |
| --- | --- | --- | --- |
| Recharts setup + custom dark theme config | High | Low | Recharts theme, axis styles |
| MidPrice LineChart with bid/ask overlays | High | High | charts/MidPriceChart.jsx |
| Order book shaded band (ReferenceArea) | Med | Med | Part of MidPriceChart |
| MarketData table (order book snapshots) | High | Low | panels/MarketDataTable.jsx |
| FundingRate BarChart (green/red by sign) | High | Med | charts/FundingRateChart.jsx |
| MarketData.jsx — compose all panels | High | Low | views/MarketData.jsx |
| FillRate BarChart (BUY/SELL grouped) | High | Med | charts/FillRateChart.jsx |
| FillHistory table (sortable, all fills) | High | Med | panels/FillHistory.jsx |
| FillStatistics sidebar cards | Med | Low | panels/FillStats.jsx |
| Fills.jsx — compose all panels | High | Low | views/Fills.jsx |
| CumulativePnL LineChart (fill above/below zero) | High | High | charts/PnLChart.jsx |
| PnL breakdown table (per-fill contributions) | High | Low | panels/PnLBreakdown.jsx |
| KPI cards (annualized return, drawdown, etc.) | High | Med | panels/KpiCards.jsx |
| PnL.jsx — compose all panels | High | Low | views/PnL.jsx |

✓ Exit Criteria All charts render with real data from the backend Mid price chart correctly overlays bid/ask from order book Cumulative PnL chart shows green/red fill relative to zero Funding rate bars colored correctly by sign Fill history table is sortable by timestamp (default: newest first) KPI cards display formatted values from /kpis endpoint

| Sprint 5 ● 1–2 days Settings View, Polish & Design QA | REFINEMENT SPRINT |
| --- | --- |

Build the Settings/Info view and do a full visual and functional pass across all views. This is the sprint where the app goes from "works" to "looks professional." Use the Bloomberg Terminal / TradingView dark aesthetic as the bar to clear.

### Settings View Panels

- Current Configuration — read-only display of strategy, symbol, spread, quote size, max inventory, poll interval

- Database Stats — record counts per table, database size

- About — app version, backend URL, optional GitHub link

### Polish Checklist

- Typography: all prices in JetBrains Mono, all labels in Inter

- Spacing: consistent card padding, no unexpected whitespace

- Sign coloring: green positive, red negative, no exceptions

- Status dots: no false positives or negatives — review staleness logic

- Loading skeletons render before data arrives on all panels

- Error states with retry visible on all panels

- Subtle spinner in panel corner while fetching

- "Last updated: Xs ago" shown on all data panels

- Sidebar tooltips on hover for all icon nav items

### Task Breakdown

| Task | Priority | Complexity | Output |
| --- | --- | --- | --- |
| Settings.jsx with all three panels | Med | Low | views/Settings.jsx |
| Config display panel (read-only) | Med | Low | panels/ConfigInfo.jsx |
| DB stats panel (record counts per table) | Low | Low | panels/DbStats.jsx |
| Typography audit — monospace/sans-serif enforcement | High | Low | CSS review |
| Color audit — green/red/blue/purple consistency | High | Low | CSS review |
| Loading skeleton on every panel | High | Low | components/common/LoadingState.jsx |
| Error state + retry on every panel | High | Low | components/common/ErrorState.jsx |
| Sidebar tooltip labels on hover | Med | Low | Sidebar nav |
| Stale data indicator (yellow border on old panels) | Med | Med | Data layer |
| Full viewport QA at 1440x900 | High | Low | QA pass |

✓ Exit Criteria Settings view renders all three panels with live data All 6 views reviewed at 1440x900 — no layout breaks Loading and error states tested by stopping the backend All prices in monospace font Sign coloring correct on all PnL and price fields

| Sprint 6 ● 1–2 days PyWebView Packaging & Launch Script | FINAL DELIVERY |
| --- | --- |

Package the app as a native desktop window. After this sprint the user runs one command — python launch.py — and a native window opens with no browser tab and no visible terminal. Production build is served directly by FastAPI.

### Task Breakdown

| Task | Priority | Complexity | Output |
| --- | --- | --- | --- |
| npm run build — Vite production build to dist/ | High | Low | apps/dashboard/frontend/dist/ |
| FastAPI StaticFiles mount for dist/ at root | High | Low | apps/dashboard/main.py (add mount) |
| launch.py — start uvicorn as subprocess | High | Med | launch.py at repo root |
| launch.py — health check loop (30 retries x 0.5s) | High | Low | Part of launch.py |
| launch.py — pywebview.create_window() | High | Low | Part of launch.py |
| launch.py — terminate subprocess on window close | High | Low | Part of launch.py |
| pywebview added to pyproject.toml dependencies | High | Low | pyproject.toml |
| CORS restricted to localhost in production build | Med | Low | apps/dashboard/main.py |
| Test cold start: python launch.py from clean shell | High | Low | Manual test |
| Test window close: backend process terminates cleanly | High | Low | Manual test |
| Document launch steps in README.md | Med | Low | README.md update |

✓ Exit Criteria python launch.py opens a native OS window on Windows 10/11 No browser tab opens — PyWebView window only Backend process terminates when window is closed Production build serves correctly from FastAPI StaticFiles Full app functions identically in packaged mode as in dev

# Guiding Principles for This Build

These carry over from the project scope and should be kept in mind throughout every sprint:

- Read-only only — no controls that modify system state, no kill switches, no config edits

- Never block on missing data — show last known value + stale indicator, not a blank panel

- account_name filter — always filter position/fill queries by "paper_mm"

- NUMERIC precision — all financial values arrive as strings; format 2dp for USD, 8dp for BTC

- Timestamps always UTC from DB — convert to local time before display

- 120s staleness rule — order book data older than 2 minutes must be visually flagged

- No authentication layer — this is a local app, no login screens ever

- Windows 10/11 is the primary target for PyWebView packaging

# Sprint Dependency Map

Sprints must be completed in order. Each sprint depends on the previous.

| Sprint | Depends On | Unblocks |
| --- | --- | --- |
| Sprint 1 | Nothing | Sprint 2 (component library must exist before hooking up data) |
| Sprint 2 | Sprint 1 (app shell, component primitives) | Sprints 3, 4, 5 (all views depend on hooks) |
| Sprint 3 | Sprint 2 (data hooks) | Can be validated as first live views |
| Sprint 4 | Sprint 2 (data hooks), Sprint 1 (DataTable, ChartContainer) | Sprint 5 (polish pass needs all views built) |
| Sprint 5 | Sprints 3 and 4 (all views must exist) | Sprint 6 (packaging requires finished app) |
| Sprint 6 | Sprint 5 (complete, polished app) | Final delivery |

crypto-mvp Dashboard Roadmap  ·  Phase 6 of the project scope  ·  Total estimate: 12–17 days